OFFICE OF THE POLICE & CRIME COMMISSIONER FOR SURREY & SURREY POLICE
Internal Audit Progress Report October 2023

Contents:

1.	Purpose of report	3
2.	Performance dashboard	4
3.	Analysis of ‘Live’ audit reviews	6
4.	Rolling work programme	8
Annexe 1	Pre 2020-21 Audit Opinion Definitions	13

Purpose of report

Internal audit reviews culminate in an opinion on the assurance that can be placed on the effectiveness of the framework of risk management, control and governance designed to support the achievement of management objectives of the service area under review.

CIPFA have recommended standardising the terminology and definitions used in internal audit engagements across the whole of the public sector and have published a standard set of opinions and supporting definitions for internal audit service providers to use. To ensure we continue to conform to the best practice principles, we have adopted the standard definitions. The assurance opinions are categorised as follows:

* Some reports listed within this progress report (pre 2020/21 audit plan) refer to categorisations used by SIAP prior to adoption of the CIPFA standard definitions, reference is provided at Annex 1 on page 12.

Performance dashboard

10 %
Complete
18 % of
revised plan delivered to to least draft report
55 %
Work in Progress
35 %
Yet to Commence
	Stakeholder Satisfaction Survey Results
100%
98%
96%
94%
92%
90%
88%
86%
84% / Target		Actual

Days Delivered

	Surrey 2023/24 plan	Joint Sussex and Surrey / 2023/24 plan
Original Plan Days	107	333
Revised Plan Days	107	348
Days delivered	31	113
Percentage of revised / plan delivered	29%	33%

Compliance with Public Sector Internal Audit Standards
An External Quality Assessment of the Southern Internal Audit Partnership was undertaken by the Institute of Internal Auditors (IIA) in September 2020. The report concluded:
‘The mandatory elements of the IPPF include the Definition of Internal Auditing, Code of Ethics, Core Principles and International Standards. There are 64 fundamental principles to achieve with 118 points of recommended practice. We assess against the principles.
It is our view that the Southern Internal Audit Partnership conforms to all 64 of these principles.
We have also reviewed SIAP conformance with the Public Sector Internal Audit Standards (PSIAS) and Local Government Application Note (LGAN).
We are pleased to report that SIAP conform with all relevant, associated elements.’

Analysis of ‘Live’ audit reviews (as at 5 October)
Audit Review	Report Date	Audit Sponsor	Assurance Opinion	Total Management / Action(s)	Not Accepted	Not Yet Due	Complete/ Retired**	Overdue
								L	M	H
Benefits Realisation from Investment	10.01.20	CFO OPCC & EDCFS	Adequate	4	0	0	2		2
IT Systems Lifecycle Support and / Planning	10.05.21	CDIO	Reasonable	8	0	0	7		1
Transport – Fleet Management	24.02.22	CFO OPCC / & EDCFS	Reasonable	6	0	0	5		1
IT Virtualisation	18.05.22	CDIO	Limited	8	0	0	6		2
Network Management	13.06.22	CDIO	Reasonable	11	0	0	9		2
Application Management – Niche*	14.06.22	CDIO	Reasonable	5	0	0	5
ERP – Legacy IT Risks Oracle People / Solutions	07.07.22	CDIO	No Assurance	11	0	9	1			1
Strategy and arrangements for delivery of training to meet future / need	22.08.22	CFO OPCC & EDCFS	Reasonable	4	0	0	3		1
Seized property and cash	23.08.22	CFO OPCC / & EDCFS	Reasonable	15	0	0	12	1	2
Revenue Contract Management*	23.08.22	CFO OPCC / & EDCFS	Reasonable	4	0	0	4
Duty Resource Planning	15.09.22	CFO OPCC / & EDCFS	Limited	9	0	4	5
Operating Systems Management	06.12.22	CDIO	Limited	17	0	0	16		1
Uniform Control*	21.02.23	CFO OPCC / & EDCFS	Limited	3	0	0	3
IT Service Desk	09.05.23	CDIO	Reasonable	5	0	1	4
Firearms Licencing	25.05.23	CFO	Reasonable	4	3	0	1

Risk Management	20.06.23	CFO OPCC / & EDCFS	Reasonable	12	0	4	4	2	2
Mobile Handheld Devices	26.06.23	CDIO	Reasonable	3	0	2	1
Accounts Receivable	28.06.23	CFO OPCC / & EDCFS	Limited	6	0	0	4	1		1
Vulnerability Management	03.07.23	CDIO	Reasonable	12	0	2	0	9	1
Forensic Collision Investigation Unit – / ISO Accreditation	20.07.23	EDCFS	Reasonable	5	0	0	4		1
Pensions Contract Management*	12.09.23	EDCFS	Substantial	0	0	0	0
Database Management	26.09.23	CDIO	Limited	21	0	15	4		2
Victims Code Compliance	04.10.23	CFO (CC) & / CFO (OPCC)	Reasonable	11	0	9	2
Accounts Payable	04.10.23	EDCFS	Reasonable	6	0	0	3	2		1
Total								15	18	3

* Denotes audits where all actions have been completed since the last progress report.
** Denotes where actions are retired/pending retirement.

Audit Sponsor (Director)
Chief Finance Officer	CFO
Executive Director for Commercial & Financial Services	EDCFS
Chief Digital Information Officer	CDIO

Rolling Work Programme

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report / Issued	Assurance Opinion	Comment / previous opinion
Audit Plan 2022/23
Surrey Police Plan
Accounts Payable	EDCFS				04 & / 27.04.23	04.10.23	Reasonable
Shared Plan with Sussex Police
Pensions Contract Management	EDCFS				06.07.23	12.09.23	Substantial
Database Management	CD&IO				11.07.23	26.09.23	Limited
Audit Plan 2023/24
Surrey Police Plan
Victims Code Compliance	CFO (CC) & CFO (OPCC)				13.09.23	03.10.23	Reasonable
Unsocial Hours	CFO (CC)							Close meeting 14 Sept. / Advisory/ First review
				
Surrey Safer Roads Partnership	CFO (CC)							Q2 / First review
Child Exploitation	CFO (CC)							Scoping meeting 20 Sept / First review
		
Payroll	CFO (CC)							Q3 / Reasonable

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report / Issued	Assurance Opinion	Comment / previous opinion
Perpetrator Pathways – Domestic Abuse	CFO (CC)							Q3 / First review
Management of Sexual or Violent Offenders	CFO (CC)							Q3 / First review
Estates Strategy and Disposals	CFO (CC)							Q4 / Substantial
Shared Plan with Sussex Police
Estates and facilities management	CFO (CC) & CFO (OPCC)							Fieldwork underway / Limited
				
Forensic Collision Investigation Unit – / ISO Accreditation	CFO (CC)
					11.07.23	20.07.23	Reasonable
Health and Safety	CFO (CC)							Fieldwork underway / Reasonable
				
Leavers process	CFO (CC)							Delay in receiving management actions from across the Force First review
					14.07.23
Occupational Health Recharging	CFO (CC)							Additional testing underway following review process. / First review
				
PEQF – Protected Learning	CFO (CC)							Draft final issued 05.10.23
					27.09.23

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report / Issued	Assurance Opinion	Comment / previous opinion
First review
Redundancy process and payments	CFO (CC)							Draft ToR issued 30 Aug – under discussion with the business lead. / First review
		
Vehicle Recovery Process	CFO (CC)							Additional testing underway following review process. / First review
				
ICT Assurance Mapping and Coverage Analysis Based on ITIL 4 Practices	CD&IO
			N/A		25.08.23	12.09.23	N/A
Government Procurement Cards	CFO (CC)							Fieldwork underway / Substantial
				
Flexible Retirements	CFO (CC)							To commence end of Q3 due to the team’s operational capacity. / First review
Joint Force Vetting Unit	CFO (CC)							Scoping held 2 Aug, audit moved from Q2 to Q4 at request of DCCs. Start date 8 Jan 2024 / Reasonable
		

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report / Issued	Assurance Opinion	Comment / previous opinion
Effectiveness of Collaborative Arrangements	CFO (CC)							Scoping meetings 26 Oct & 1 Nov. / First review
		
Business Continuity Planning	CFO (CC)							Scoping booked 10 Oct / Reasonable
		
Armouries	CFO (CC)							Scoping meeting 9 Oct. / First review.
		
IT Contingency for Outcomes of Assurance Mapping	CD&IO							Linked to Q1 mapping activity / covered in separate report
Learning and Development / Mandatory Training	CFO (CC)							Q4 / First review
Contract management - capital	CFO (CC)							Q4 / First review
Change Governance and Benefits Realisation	CFO (CC)							Q4 / First review
Data Protection Impact Assessments	CFO (CC)							Q4 / First review

The following variations have been made to the 2023/24 internal audit plan since it was presented to the Joint Audit Committee in April 2023

Audit reviews removed from the 2023/24 plan
Shared Plan - Eye Care Scheme (Q4) (Joint review)	Removed as data has confirmed this as low risk. Days from this review have been incorporated into the Joint Vetting audit, subject to discussion with the DCCs regarding scope.
Annual Governance Statement – OPCC (Q3) *	Removed from the plan as considered lower risk, days used to support the addition of the joint Armouries audit to the plan.
Audit reviews added to the 2023/24 plan
Unsocial Hours (Surrey only review)	Added to the plan in May 2023 as an advisory piece of work to support improving the control environment and to review the approach taken to review unsocial hours claims. Victims Code audit moved to Q2 to accommodate.
Shared Plan - Armouries (Q3) *	Added to the plan following an HMICFRS recommendation for an independent annual audit.

* Denotes variations since the last report to the Joint Audit Committee.

Annex 1 - Assurance opinions and definitions used by SIAP prior to adoption of the CIPFA standard definitions

Substantial	A sound framework of internal control is in place and operating effectively. No risks to the achievement of system objectives have been / identified
Adequate	Basically, a sound framework of internal control with opportunities to improve controls and / or compliance with the control framework. No significant risks to the achievement of system objectives have been identified
Limited	Significant weakness identified in the framework of internal control and / or compliance with the control framework which could place the achievement of system objectives at risk
No	Fundamental weaknesses identified in the framework of internal control or the framework is ineffective or absent with significant risk to the achievement of system objectives.