OFFICE OF THE POLICE & CRIME COMMISSIONER FOR SURREY & SURREY POLICE
Internal Audit Progress Report June 2024

Contents:

1.	Purpose of report	3
2.	Performance dashboard	4
3.	Analysis of ‘Live’ audit reviews	6
4.	Rolling work programme	8
Annexe 1	Pre 2020-21 Audit Opinion Definitions	14

Purpose of report
Internal audit reviews culminate in an opinion on the assurance that can be placed on the effectiveness of the framework of risk management, control and governance designed to support the achievement of management objectives of the service area under review.

CIPFA have recommended standardising the terminology and definitions used in internal audit engagements across the whole of the public sector and have published a standard set of opinions and supporting definitions for internal audit service providers to use. To ensure we continue to conform to the best practice principles, we have adopted the standard definitions. The assurance opinions are categorised as follows:

* Some reports listed within this progress report (pre 2020/21 audit plan) refer to categorisations used by SIAP prior to adoption of the CIPFA standard definitions, reference is provided at Annex 1 on page 12.

Performance dashboard

75%
Complete
93% of
revised plan delivered to to least draft report
25%
Work in Progress
0%
Yet to Commence
	Stakeholder Satisfaction Survey Results
100%
98%
96%
94%
92%
90%
88%
86%
84% / Target		Actual

Days Delivered

	Surrey 2023/24 plan	Joint Sussex and Surrey / 2023/24 plan
Original Plan Days	107	333
Revised Plan Days	102	323
Days delivered	102	317
Percentage of revised / plan delivered	100%	98%

Compliance with Public Sector Internal Audit Standards
An External Quality Assessment of the Southern Internal Audit Partnership was undertaken by the Institute of Internal Auditors (IIA) in September 2020. The report concluded:
‘The mandatory elements of the IPPF include the Definition of Internal Auditing, Code of Ethics, Core Principles and International Standards. There are 64 fundamental principles to achieve with 118 points of recommended practice. We assess against the principles.
It is our view that the Southern Internal Audit Partnership conforms to all 64 of these principles.
We have also reviewed SIAP conformance with the Public Sector Internal Audit Standards (PSIAS) and Local Government Application Note (LGAN).
We are pleased to report that SIAP conform with all relevant, associated elements.’
Analysis of ‘Live’ audit reviews (as at 5 June)
Audit Review	Report Date	Audit Sponsor	Assurance Opinion	Total Management / Action(s)	Not Accepted	Not Yet Due	Complete/ Retired**	Overdue
								L	M	H
Benefits Realisation from Investment	Jan 20	CFO (CC & OPCC)	Adequate	4	0	0	2		2
IT Systems Lifecycle Support and / Planning*	May 21	CDIO	Reasonable	8	0	0	8
Transport – Fleet Management	Feb 22	ACC	Reasonable	6	0	0	5		1
IT Virtualisation	May 22	CDIO	Limited	8	0	0	6		2
ERP – Legacy IT Risks Oracle People / Solutions	Sep 22	CDIO	No Assurance	11	0	9	2
Strategy and arrangements for delivery of training to meet future / need	Aug 22	DPS	Reasonable	4	0	0	3		1
Seized property and cash*	Aug 22	ACC	Reasonable	15	0	0	15
Contract Management (Revenue)*	Aug 23	CFO (CC)	Reasonable	4	0	0	4
Duty Resource Planning	Sep 22	ACC	Limited	9	0	0	5	1	2	1
Operating Systems Management	Dec 22	CDIO	Limited	17	0	0	16		1
IT Service Desk	May 23	CDIO	Reasonable	5	0	0	4		1
Risk Management	Jun 23	DCC	Reasonable	12	0	0	10	1	1
Vunerablity Management	Jul 23	CDIO	Reasonable	12	0	1	11
Database Management	Sep 23	CDIO	Limited	21	0	0	20		1
SSP Leavers*	Dec 23	DPS	Limited	14	0	0	14
SSP Vehicle Recovery Process	Jan 24	ACC	Limited	11	0	3	7	1
SSP Armouries (storage and / management)	Feb 24	ACC	Limited	13	0	4	9
SSP Business Continuity (SAP/ Oracle)	Feb 24	CFO (CC)	Limited	14	0	2	11	1

Surrey Payroll	Feb 24	CFO (CC)	Reasonable	5	0	2	3
SSP Government Procurement Cards	Apr 24	CFO (CC)	Limited	4	0	2	2
Surrey RoadSafe Partnership	Apr 24	ACC	Reasonable	11	0	5	0	1	5
SSP Estates and Facilities Management	May 24	CFO (CC)	Limited	16	0	15	0		1
SSP Governance and Monitoring of / Collaborative Arrangements*	May 24	DCC	Reasonable	2	0	0	2
SSP Contract Management - Capital	May 24	CFO (CC)	Reasonable	3	0	3	0
SSP Change Governance and Benefits / Realisation	May 24	DCC	Reasonable	6	0	3	1	1	1
Sussex Governance of Local Policing / Engagement	May 24	DCC	Reasonable	1	0	1	0
SSP Redundancy Process and / Payments	May 24	DoPS	Limited	8	0	2	6
SSP IT Major Incident Management	Jun 24	CDIO	Reasonable	6	0	6	0
Total								6	19	1

* Denotes audits where all actions have been completed since the last progress report.
** Denotes where actions are retired/pending retirement.

Audit Sponsor (Director)
Chief Finance Officer	CFO
Deputy Chief Constable	DCC
Assistant Chief Constable	ACC
ACO Chief Digital Information Officer	CDIO
ACO Director People Services	DPS

Rolling Work Programme

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report Issued	Assurance Opinion	Comment / previous opinion
Audit Plan 2022/23
Shared Plan with Sussex Police
Database Management	CD&IO				11.07.23	26.09.23	Limited
Audit Plan 2023/24
Surrey Police Plan
Victims Code Compliance	ACC & OPCC				13.09.23	03.10.23	Reasonable
Unsocial Hours	DPS				25.10.23	08.01.24	N/A	Advisory
Surrey RoadSafe Partnership	ACC				19.03.24	08.04.24	Reasonable
Payroll	DPS				13.02.24	28.02.24	Reasonable
Perpetrator Pathways – Domestic Abuse – Governance and Roles & Responsibilities	ACC				23.05.24			Draft final report issued 13 Jun
Surrey - Data Storage and Backup	CD&IO				31.03.24			Awaiting management responses
Shared Plan with Sussex Police

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report Issued	Assurance Opinion	Comment / previous opinion
Estates and facilities management	DCC				05.03.24	22.05.24	Limited	Delays in holding close meeting due to availability of key contact, receiving information and management responses.
Forensic Collision Investigation Unit / – ISO Accreditation	ACC				11.07.23	20.07.23	Reasonable
Health and Safety	DCC				14.12.23	31.01.24	Reasonable
Leavers process	DPS				14.07.23	14.12.23	Limited	Delays in receiving management actions
Occupational Health Recharging	DPS				17.10.23	14.11.23	Limited
PEQF – Protected Learning	DPS				27.09.23	26.10.23	Reasonable
Redundancy process and payments	DPS				15.04.24	28.05.24	Limited	Delayed from Q1 due to Force operational capacity. / Additional testing undertaken following close meeting. Delays in obtaining management actions.

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report Issued	Assurance Opinion	Comment / previous opinion
Vehicle Recovery Process	ACC				27.11.23	12.01.23	Limited	Delays in obtaining management actions
ICT Assurance Mapping and Coverage Analysis Based on ITIL 4 Practices	CD&IO		N/A		25.08.23	12.09.23	N/A
Government Procurement Cards	CFO (CC)				09.04.24	23.04.24	Limited	Delays due to HCC IT Firewall issues – site visits undertaken. Delay in holding close meeting due to key contact availability
Flexible Retirements	ACC				29.05.24			Moved from Q2 due to Force operational capacity. Delays in obtaining evidence due to the key contact leaving the Force. / Management actions due. / First review
Governance and Monitoring of Collaborative Arrangements	DCC				13.03.24	22.05.24	Reasonable	Delayed start due to number of senior

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report Issued	Assurance Opinion	Comment / previous opinion
stakeholders involved. / Delays receiving management actions.
Business Continuity (SAP/ Oracle)	CFO (CC)				24.01.24	29.02.24	Limited
Armouries	ACC				17.01.24	28.02.24	Limited
Legacy Application Management	CD&IO							Testing underway First review
Learning and Development / Mandatory Training	ACC				30.05.24	07.06.24	Limited
Contract management - capital	ACC				23.04.24	23.05.24	Reasonable	Delay is issuing final due to additional information provided following draft report
Change Governance and Benefits Realisation	DCC				22.04.24	07.05.24	Reasonable
Data Protection Impact Assessments	DCC							Testing underway, close meeting cancelled on 30 May, due to additional testing required. / First review

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report Issued	Assurance Opinion	Comment / previous opinion
Supply Chain Security Management	CD&IO				07.06.24			Awaiting management actions. First review
Major Incident Management	CD&IO				15.04.24	07.06.24	Reasonable	Delays in receiving management actions.
IT Follow Up	CD&IO				11.06.24			Draft report issued

The following variations have been made to the 2023/24 internal audit plan since it was presented to the Joint Audit Committee in April 2023 and changes since the last JAC meeting are marked with *.

Audit reviews removed from the 2023/24 plan
Shared Plan - Eye Care Scheme (Q4) (Joint review)	Removed as data has confirmed this as low risk.
Annual Governance Statement – OPCC (Q3)	Removed from the plan as considered lower risk, days used to support the addition of the joint Armouries audit to the plan.
Estates Strategy and Disposals (Q4)	Deferred to 2024-25 due to delays in the project and to align planned audit coverage with stages reached.
Shared Plan - Trend Micro Deep Security Management	Removed from plan as the underlying reason for using Trend is being addressed by Operation Yorton. The days have been used on the two Data Storage and Backup audits, which was originally one shared review.
Shared Plan - Data Storage and Backup	Due to differences in technology and procedures used between Sussex and Surrey this will be treated as two separate reviews with two reports.

Shared Plan - Joint Force Vetting Unit	Request to defer the audit by the DCCs in Q4 when fieldwork was commencing due to clash with HMICFRS inspection preparation. To be undertaken in Q4 2024-25.
Management of Sexual or Violent / Offenders (Q4)	Removed from plan as covered in a recent HMIC inspection.
Child Protection – Strategy & Governance (Q4) *	Removed from the plan due to a scheduling conflict with the upcoming HMIC inspection.
Audit reviews added to the 2023/24 plan
Unsocial Hours (Surrey only review)	Added to the plan in May 2023 as an advisory piece of work to support improving the control environment and to review the approach taken to review unsocial hours claims. Victims Code audit moved to Q2 to accommodate.
Shared Plan - Armouries (Q3)	Added to the plan following an HMICFRS recommendation for an independent annual audit.
Shared Plan - IT Audits: / Data Storage and Backup Trend Micro Deep Security Management / Legacy Application Management Supply Chain Security Management / Major Incident Management IT Follow Up	Added to the plan in September following agreement of the IT internal audit strategy report which included ITIL assurance mapping.
Surrey - Data Storage and Backup	Due to differences in technology and procedures used between Sussex and Surrey this will be treated as two separate reviews with two reports.

Annex 1 - Assurance opinions and definitions used by SIAP prior to adoption of the CIPFA standard definitions

Substantial	A sound framework of internal control is in place and operating effectively. No risks to the achievement of system objectives have been / identified
Adequate	Basically, a sound framework of internal control with opportunities to improve controls and / or compliance with the control framework. No significant risks to the achievement of system objectives have been identified
Limited	Significant weakness identified in the framework of internal control and / or compliance with the control framework which could place the achievement of system objectives at risk
No	Fundamental weaknesses identified in the framework of internal control or the framework is ineffective or absent with significant risk to the achievement of system objectives.