OFFICE OF THE POLICE & CRIME COMMISSIONER FOR SURREY & SURREY POLICE
Internal Audit Progress Report June 2025

Contents:
1. Purpose of report	3
2. Performance dashboard	4
3. Analysis of ‘Live’ audit reviews	6
4. Rolling work programme	9
Purpose of report
Internal audit reviews culminate in an opinion on the assurance that can be placed on the effectiveness of the framework of risk management, control and governance designed to support the achievement of management objectives of the service area under review.
CIPFA have recommended standardising the terminology and definitions used in internal audit engagements across the whole of the public sector and have published a standard set of opinions and supporting definitions for internal audit service providers to use. To ensure we continue to conform to the best practice principles, we have adopted the standard definitions. The assurance opinions are categorised as follows:

* Some reports listed within this progress report (pre 2020/21 audit plan) refer to categorisations used by SIAP prior to adoption of the CIPFA standard definitions, reference is provided at Annex 1.

Performance dashboard

68%
Complete
95% of
revised plan delivered to to least draft report
32%
Work in Progress
0%
Yet to Commence
Stakeholder Satisfaction Survey Results
100%
98%
96%
94%
92%
90%
88%
86%
84%
Target
Actual

Days Delivered

	Surrey 2024/25 plan	Joint Sussex and Surrey / 2024/25 plan
Original Plan Days	103	350
Revised Plan Days	103	263
Days delivered	103	263
Percentage of revised / plan delivered	100%	100%

Compliance with Public Sector Internal Audit Standards
An External Quality Assessment of the Southern Internal Audit Partnership was undertaken by the Institute of Internal Auditors (IIA) in September 2020. The report concluded:
‘The mandatory elements of the IPPF include the Definition of Internal Auditing, Code of Ethics, Core Principles and International Standards. There are 64 fundamental principles to achieve with 118 points of recommended practice. We assess against the principles.
It is our view that the Southern Internal Audit Partnership conforms to all 64 of these principles.
We have also reviewed SIAP conformance with the Public Sector Internal Audit Standards (PSIAS) and Local Government Application Note (LGAN).
We are pleased to report that SIAP conform with all relevant, associated elements.’
Analysis of ‘Live’ audit reviews (as at 9 June 2025)
Audit Review	Report Date	Audit Sponsor	Assurance Opinion	Total Management / Action(s)	Not Accepted	Not Yet Due	Complete/ Retired**	Overdue
								L	M	H
ERP – Legacy IT Risks Oracle People Solutions	Sep 22	COO	No Assurance	11	0	0				6
Strategy and arrangements for delivery of training to meet future / need	Aug 22	DPS	Reasonable	4	0	0	3		1
Duty Resource Planning	Sep 22	ACC	Limited	9	0	0	7		1	1
Operating Systems Management	Dec 22	COO	Limited	17	0	0	16		1
Vulnerability Management	Jul 23	COO	Reasonable	12	0	0	11	1
Database Management	Sep 23	COO	Limited	21	1**	0	18		2
SSP Vehicle Recovery Process	Jan 24	ACC	Limited	11	0	0	9	2
SSP Armouries (storage and / management)	Feb 24	ACC	Limited	13	0	1	11		1
SSP Business Continuity (SAP/ Oracle)	Feb 24	CFO	Limited	14	0	0	13	1
Surrey Payroll	Feb 24	CFO	Reasonable	5	0	1	4
Surrey RoadSafe Partnership	Apr 24	ACC	Reasonable	11	0	0	3	2	5
SSP Estates and Facilities Management	May 24	CFO	Limited	16	0	0	11	1	3	1
SSP Contract Management – Capital*	May 24	CFO	Reasonable	3	0	0	3
SSP IT Major Incident Management	Jun 24	COO	Reasonable	6	0	0	4		2
SSP Learning & Development / Mandatory Training 2023/24	June 24	DPS	Limited	6	0	2	2		1	1
Surrey Perpetrator Pathways – Domestic Abuse – Governance and / Roles & Responsibilities	Jul 24	ACC	Reasonable	3	0	0	0		3

SSP Supply Chain Security / Management	Jul 24	COO	Reasonable	14	0	1	13
Surrey - Data Storage and Backup	Jul 24	COO	Reasonable	5	0	0	2	2	1
SSP Legacy Application Management*	Nov 24	COO	Reasonable	4	0	0	4
SSP NPAS - National Air Helicopter / Service – Use of Allocated Hours	Feb 25	ACC	Reasonable	5	0	3	1		1
SSP Management of Fleet Vehicles*	Feb 25	CFO	Reasonable	2	0	0	2
SSP Crime Management – Organised / Crime Groups Processes	Feb 25	ACC	Reasonable	6	0	0	6
SSP Business Continuity – Longer Term / Planning	May 25	ACC	Limited	9	0	9	0
SSP Joint Procurement	May 25	CFO (CC)	Reasonable	3	0	3	0
SSP Dog School Income Generation	May 25	ACC	No	17	0	7	10
SSP Recruitment	May 25	ACO	Reasonable	6	0	6	0
OPCC – PCC General and Statutory / Duties*	May 25	CFO (PCC)	Substantial	0	0	0	0
Adult Abuse Investigation – / Governance and Reporting	June 25	ACC	Reasonable	3	0	3	0
Total								9	22	9

* Denotes audits where all actions have been completed since the last progress report.
** Denotes where actions are retired/pending retirement.

Audit Sponsor (Director)
Chief Finance Officer	CFO
Deputy Chief Constable	DCC
Assistant Chief Constable	ACC
Chief Operating Officer	COO
ACO Director People Services	DPS

Rolling Work Programme
# 2023/24 Audit Plan – Remaining Audits

Audit Review	Audit Sponsor	Scoping Terms of / Reference Issued	Fieldwork Draft / Report Issued	Final Report Issued	Assurance Opinion	Comment / Previous Opinion
Shared Plan with Sussex Police
Data Protection Impact Assessments	DCC	 	12.08.24	17.10.24	Reasonable
Legacy Application Management	COO	 	20.11.24	28.11.24	Reasonable

2024/25 Audit Plan

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report / Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
Collaborated Plan
Use of Air Support (Drones) - / Governance	ACC	17.06.24	02.08.24	04.11.24 / 16.12.24	21.01.25	30.01.25	Substantial	Q1
NPAS - National Air Helicopter Service – / Use of Allocated Hours	ACC	02.08.24	09.09.24	07.10.24 / 18.11.24	9.12.24	03.02.25	Reasonable	Q2
Management of Fleet Vehicles	CFO	01.08.24	05.08.24	09.09.24 / 18.11.24	15.11.24	10.02.25	Reasonable	Q2
Transformation Savings Governance	CFO	31.07.24	18.09.24	19.12.24 / 03.02.25	07.02.25	11.02.25	Substantial	Q2

Audit Review	Audit Sponsor	Scoping	Terms of / Reference Issued	Fieldwork	Draft / Report Issued	Final / Report Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
Crime Management – Organised Crime / Groups Processes	ACC	27.08.24	09.09.24	17.10.24 / 06.01.25	15.01.25	26.02.25	Reasonable	Q2
Business Continuity Planning	DCC	24.10.24	26.11.24	16.12.24 / 07.03.25	18.03.25	09.05.25	Limited	Q3	Delays were due to the late receipt and subsequent agreement of management actions.
Counter Fraud Work / - Advisory	ACC	28.10.24	09.01.24	03.03.25 / 28.03.25	N/A	12.05.25	N/A	Q3
Dog School – Income Generation	ACC	02.12.24	17.12.24	24.01.25 / 21.03.25	03.04.25	19.05.25	No	Q3
Armouries – Storage and Management	ACC	19.12.24	06.02.25	10.03.25 / 04.04.25	14.05.25		N/A	Q4	Factual accuracy of report agreed.
Recruitment	DPS	14.11.24	17.12.24	13.01.25 / 10.03.25	09.04.25	22.05.25	Reasonable	Q4
Joint Procurement	CFO	08.01.25	07.03.25	03.04.25 / 25.04.25	29.04.25	13.05.25	Reasonable	Q4
Collaborated Plan - IT
Software Licensing	COO	07.06.24	22.08.24	13.12.24 / 13.05.25				Q1	Delays to delivery caused by audit team. / First Review
Service Transition	COO	21.06.24	05.09.24	12.12.24 / 26.05.25	28.05.25		Reasonable	Q1	Factual accuracy of report agreed.

Audit Review	Audit Sponsor	Scoping	Terms of / Reference Issued	Fieldwork	Draft / Report Issued	Final / Report Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
Data Centre Facilities and Security	COO	22.01.25	06.03.25	31.03.25 / 09.05.25	16.05.25		Reasonable	Q2	Factual accuracy of report agreed. Draft final report issued 05.06.25.
Application Management NICE Investigate	COO	06.02.25	26.02.25	19.03.25 / 22.04.25	12.05.25		Limited	Q3	Factual accuracy of report agreed. Draft final report issued 09.06.25.
Surrey Plan
Estates Strategy - Redevelopment of / Mount Browne	CFO	14.05.24	02.07.24	08.10.24 / 16.12.24	21.01.25	10.02.25	Substantial	Q1
Management Information – Dashboard Development and / Use	DCC	20.05.24	22.08.24	23.09.24 / 24.10.24	13.11.24	14.01.25	Reasonable	Q1
Missing Person Compliance	ACC	23.05.24	18.06.24	16.12.24 / 02.05.25	19.05.25		Limited	Q1	Factual accuracy of report agreed.
Violence Against Women and Girls - Relentlessly / Pursuing Offenders	ACC	10.09.24	08.10.24	22.11.24 / 19.12.24	29.01.25	26.02.25	Substantial	Q2

Audit Review	Audit Sponsor	Scoping	Terms of / Reference Issued	Fieldwork	Draft / Report Issued	Final / Report Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
Right Care, Right Person	ACC	28.10.24	05.12.24	03.03.25 / 02.05.25	14.05.25		Substantial	Q3	Factual accuracy of report agreed.
PCC General and Statutory Duties – Assurance / Framework	CFO (OPCC)	04.11.24	11.12.24	31.03.25 / 18.04.25	01.05.25	12.05.25	Substantial	Q3
Adult Abuse Investigation – Governance and / Reporting	ACC	16.01.25	24.02.25	14.04.25 / 08.05.25	16.05.25	02.06.25	Reasonable	Q4

2025/26 – Quarter 1

Audit Review	Audit Sponsor	Scoping	Terms of Reference Issued	Fieldwork / 1.Start 2. complete	Draft Report Issued	Final Report Issued	Assurance Opinion	Quarter	Comment (to include close of audit date if draft not issued / flag if management response / 20 days +)
Collaborated Plan
Health and Safety	DCC	17.10.24	24.02.25	07.04.25	Q1				Moved from the 2024/25 plan. / Close of audit meeting 26 June.

Audit Review	Audit Sponsor	Scoping	Terms of Reference Issued	Fieldwork / 1.Start 2. complete	Draft Report Issued	Final Report Issued	Assurance Opinion	Quarter	Comment (to include close of audit date if draft not issued / flag if management response / 20 days +)
Estates and Facilities – Recovery Plans	CFO	23.12.24	11.02.25	27.04.25	Q1				Moved from the 2024/25 plan. / Close of audit meeting 13 June. / First review
Duty of Care Risk Assessments	ACC	23.12.24	03.02.25	01.04.25	Q1				Moved from the 2024/25 plan. Delays in obtaining DOCRAs for testing, provided on 9 May. / Close of audit booked for 24 June. / First Review
Firearms and Explosives Licensing Processes	ACC	29.04.25			Q4				Deferred from Q1 to Q4 at the request of the Force due to work underway in this area.
Driver Training	ACC	01.05.25	06.06.25		Q1				First Review
Triaging of
Intelligence -	ACC	17.04.25	02.06.25		Q1				First Review
Process and
Governance
Physical Security Arrangements	COO	02.05.25	28.05.25		Q1				First Review
Occupational Health / - Psychological Safety Screening	ACO -PS	05.06.25			Q1				Moved to Q1 on 13 May to replace the Q1 Firearms audit which has been deferred to Q4.

Audit Review	Audit Sponsor	Scoping	Terms of Reference Issued	Fieldwork / 1.Start 2. complete	Draft Report Issued	Final Report Issued	Assurance Opinion	Quarter	Comment (to include close of audit date if draft not issued / flag if management response / 20 days +)
First Review
Collaborated Plan - IT
IT Disaster Recovery and IT Service Continuity	CD&IO	26.11.24	5.12.24	20.01.25	Q1				Moved from the 2024/25 plan. / Audit testing underway / First Review
									Moved from the 2024/25 plan.
High Privilege / Access Management	CD&IO	11.12.24	15.01.25	25.03.25	Q1				Close meetings being arranged for June. / First Review
Surrey Plan
Child Protection	ACC	14.05.25			Q1				First Review
Custody Compliance	ACC	14.05.25			Q1				First Review
Contact and / Deployment - Call Grading	ACC	22.05.25			Q1				First Review

VARIATIONS TO PLAN
The following variations have been made to the 2024/25 internal audit plan since it was presented to the Joint Audit Committee in April 2024 and changes since the last JAC meeting are marked with *.

Collaborated Plan
Audit reviews removed from the plan
Violence Against Women and Girls - relentlessly pursuing offenders	Removed from the SSP plan to be considered under individual force plans due to differences in processes in this area. Propose to undertake Surrey audit in Q3 and undertake Sussex in either Q4 or 2025/26.
Joint Force Vetting	Audit cancelled in October due to clash with HMICFRS inspection, along with the Angiolini Inquiry in Sussex examining some of the same areas. Propose to undertake in 2025/26 with a focus on areas for improvements identified by the inspections.
IT Health Check Remediation	Audit removed from the 2024/25 plan as the Health Check has only just started so there would not be enough to audit at the current time. The audit will be undertaken as part of the 2025/26 audit plan.
Duty of Care Risk Assessments* Health and Safety* / Estates and Facilities – Recovery Plans* High Privilege Access Management* / IT Disaster Recovery and IT Service Continuity*	Following a recommendation from the Sussex JAC, supported by the Surrey JAC and approved by the S151 Officers in the OPCCs and for the Force, these audits had a longer delivery timeframe, so have been removed from the 2024/25 plan and added to the 2025/26 plan, with the 2025/26 plan being reprofiled accordingly.
Audit reviews added to the plan
None

Surrey Police Plan
Audit reviews removed from the plan
None
Audit reviews added to the plan
Violence Against Women and Girls - relentlessly pursuing offenders	Moved from the SSP plan to the Surrey plan due to difference in processes between Surrey and Sussex.