   Agenda Item No. 07b
To:	Joint Audit Committee

Date:	23 June 2025

By:	Chief Internal Auditor

Title:	Revised Internal Audit Risk-Based Plan 2025-26

­­­­­­­­­­­­­­
Purpose of Report: The purpose of this report is to provide the Joint Audit Committee with the revised Internal Audit Risk-Based Plans for 2025–2026.

Requirement of the JAC

The Joint Audit Committee are invited to consider and make recommendation(s) as appropriate regarding the revised Internal Audit Risk-Based Plan 2025-26.

Executive Summary

Background

At the March 2025 meeting, the Joint Audit Committee requested that the Chief Internal Auditor review the delivery status of the 2024-25 audit plan and consider whether audits with extended delivery timeframes should be deferred to the 2025-26 plan. This report outlines the outcome of that review and presents the revised plan, finalised in May.

Review and Consultation

Following the meeting, a detailed analysis of the delivery status of all audits was undertaken, including root cause analysis and risk assessment. This was shared with the Section 151 Officers for Surrey and Sussex Police, Surrey OPCC and Sussex OPCC due to the collaborative nature of the plan, and their views were sought on the proposed way forward.

Key findings included:
- 8 audits were at the reporting stage and expected to be completed by end of April.
- 14 audits were in progress with varying degrees of delay, primarily due to:
  - Delayed starts by clients.
  - Resourcing challenges (e.g. vacancies, sickness) affecting both client and partnership teams.
  - Complex scoping or access issues.

Reprofiling

To ensure a balanced and achievable plan, and to support the annual audit opinion, the following approach was proposed:
- Retain audits in the current year’s plan, where delivery by end of May is feasible.
- Move five audits to the 2025-26 plan, where delivery is unlikely due to complexity, access issues, or client resourcing constraints.

The audits which were moved are:
1. Duty of Care Risk Assessments
2. Health and Safety
3. Estates and Facilities – Recovery Plans
4. SSP High Privilege Access Management
5. IT Disaster Recovery and IT Service Continuity

These audits are being undertaking in Quarter 1 of the 2025-26 plan.

The audits which were removed from the 2025-26 plan, and added to the contingency list of engagement are:
1. IT Health Check Remediation
2. High Privilege Access Management (part 2)
3. Health and Safety Governance
4. Overtime and TOIL
5. Organisational Learning

Meaning they may be undertaken if capacity allows or if emerging risks reprioritise them.
Assurance and Mitigation
The revised plan maintains sufficient coverage to support the Chief Internal Auditor’s annual conclusion. IT audit coverage has been preserved to meet assurance requirements, and recruitment is ongoing to strengthen the audit team.

Lessons learned from this year’s delivery challenges have informed the following mitigation actions:
- Earlier escalation of delays or deferrals.
- Stronger emphasis on adherence to agreed timelines.
- Improved communication with auditees.
- Engagement with senior leadership via the Organisational Reassurance Board to reinforce audit dependencies.

The revised plan remains aligned with strategic objectives and audit standards. The audit plan will remain fluid to ensure internal audit’s ability to react to the changing needs of the OPCC and Force.

Any changes to the plan will be transparently reported to the Management Team and the Joint Audit Committee during the course of the year as part of our regular progress reports.

Penny Knowles
Chief Internal Auditor
Southern Internal Audit Partnership
Penny.knowles@hants.gov.uk

Appendices

Appendix A – Risk-Based Internal Audit Plan 2024-25